## Slide 1: Soil Erosion and Torrential Flood Prevention: Curriculum Development at the Universities of Western Balkan Countries
Action plan for the next six months
(November 15th, 2019 – May 15th, 2020)
Project coordinator: University of Belgrade

## Slide 2: WORKPLAN for project year 2
Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | Analysis state of soil degradation/soil erosion in WBC | 0 |  |  |  |  |  |  |  |  |  |  |  | 
1.2 | Analysis of torrential floods in WBC | 0 |  |  |  |  |  |  |  |  |  |  |  | 
1.3 | Report of prevention measures for soil and torrent in EU | 0 |  |  |  |  |  |  |  |  |  |  |  | 
1.4 | Analysis and elaboration of bacherol and master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
1.5 | Workshop on bach. and master curricula in EU | 0 |  |  |  |  |  |  |  |  |  |  |  | 
2.1 | Defined study requirements with Bologna standards | 0 |  |  |  |  |  |  |  |  |  |  |  | 
2.2 | Defined goals, competences and learning outcomes | 0 |  |  |  |  |  |  |  |  |  |  |  | 
2.3 | Established new and improved existing subjects | 6 | 2X | 2X | 2X |  |  |  |  |  |  |  |  | 
2.4 | Established new master programme | 18 | 3X | 3X | 3X | 3X | 3X | 3X |  |  |  |  |  | 
2.5 | Study visits EU partners and analysis best practices | 4 |  |  |  |  | 2= | 2= |  |  |  |  |  | 
2.6 | Harmonization of the proposed changes | 6 | X | X | X | X | X | X |  |  |  |  |  | 
2.7 | Introduce and training teaching staff | 3 |  |  |  |  |  |  | X= | X= | X= |  |  | 
3.1 | New bachelor subjects implemented | 0 |  |  |  |  |  |  |  |  |  |  |  | 
3.2 | New master programme implemented | 0 |  |  |  |  |  |  |  |  |  |  |  | 
3.3 | Evaluation of syllabi | 0 |  |  |  |  |  |  |  |  |  |  |  | 
3.4 | Report of bachelor and master curricula quality | 4 |  |  |  |  | 2X= |  |  |  |  |  |  | 2X=
4.1 | Quality plan established | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.2 | Quality control according to the adopted plan | 4 |  |  |  |  |  |  |  |  | X= | X= | X= | X=
4.3 | External financial control | 2 |  |  |  |  |  |  |  |  |  |  | X= | X=
4.4 | Quality assurance Committee meetings | 4 |  |  |  |  |  | 2X= |  |  |  |  |  | 2X=
5.1 | Project website created and maintenance | 12 | X | X | X | X | X | X | X | X | X | X | X | X
5.2 | Establish dissemination plan | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.3 | Promotion material created | 6 |  |  |  |  |  |  | X | X | X | X | X | X
5.4 | Trainings plan defined and adopted | 6 |  |  |  |  |  |  | X= | X= | X | X | X | X
5.5 | Promotion trainings with engineers in enterprises | 3 |  |  |  |  |  |  |  |  |  | X | X | X
5.6 | Trainings in local communities | 2 |  |  |  |  |  |  |  |  |  |  | X | X
6.1 | Sustainability plan created | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.2 | Accreditation of master curricula | 24 |  |  |  |  |  |  | 4X | 4X | 4X | 4X | 4X | 4X
6.3 | Promotion for students enrollment | 4 |  |  |  |  |  |  | X | X | X | X |  | 
7.1 | Project menagement meetings | 2 |  |  |  |  |  | X= |  |  |  |  |  | X=
7.2 | Steering committee meetings | 2 |  |  |  |  |  | X= |  |  |  |  |  | X=
7.3 | Guidelines on the reporting and correspodence | 0 |  |  |  |  |  |  |  |  |  |  |  | 
7.4 | Day–to-day coordination of project activities | 22 | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | X= | X= | 2X= | 2X=
7.5 | Interim and finale report meeting | 10 |  |  |  |  | 3X= | 3X= | 2X= | 2X= |  |  |  | 
Notes: Wokplan for project realization was provided in Aplication form.
Here you can see workplan for the 2nd year of the project and especially activities planned in the next 6 monts.

## Slide 3
WP 2 – DEVELOPMENT Development of curricula |  | 
2.3 | Established new and improved existing subjects on bachelor | 
 | Report of established new and improved existing subjects on bachelor - UNS in cooperation with other partner institutions | 15.07.2019-15.03.2020
2.4 | Established new master programme | 
 | Report of establiched new master programme | 15.07.2019-15.05.2020
2.5 | Study visits EU partners and analysis best practices | 
 | Report of the study visit | 15.02.2020 – 15.09.2020
2.6 | Harmonization of the proposed changes | 
 | Report of the harmonization of the proposed changes | 15.07.2019 – 15.05.2020
Notes: WP2 Development of the curricula has six activities. Two activities were finished this year. Report on comliance requirements with Bologna (activity 2.1) was finished in September 2019. The activity 2.2. Defined goals, competence and learning outcomes finished by November 2019.
The next two activities begin in this year but they end in 2020.

## Slide 4
WP 3 – DEVELOPMENT Implementation of developed curricula and training |  | 
3.4 | Report of bachelor and master curricula quality | 
 | Report of curricula quality | 15.03.2020

## Slide 5
WP4 QUALITY PLAN Quality plan and monitoring |  | 
4.4 | Quality assurance Committee meeting | 
 | Minutes of the Quallity assurence Committee meeting- UNIRC in consultation with other participating institutions UB, UNSCM, FRI-BAS | 15.05.2020
Notes: The implementation of the activities of WP4 was delayed due to the approval of the amendment for partner replacement. 1st Quality Assurence Committee meeting was held on October 2 in Reggio Calabria, 2nd Quality assurance committee meeting is being held today at University in Banja Luka and 3th QAC meeting will be held in mid May in Sarajevo.

## Slide 6
WP5 - DISSEMINATION & EXPLOITATION Dissemination of project results |  | 
5.1 | Project website created and maintenance | 
 | Project website created - UB in consultation with UNI | In progress
5.3 | Promotion material created | 
 | Report of created promotion material - UNI in cooperation with UB | 15.12.2019
Notes: The website is maintained every month.
Procurement of promotion material shoud finished as soon as possible.

## Slide 7
WP6 - DISSEMINATION & EXPLOITATION Exploitation of project results |  | 
6.1 | Sustainability plan created | 
 | Report of Sustainability plan created | 15.12.2019
6.3 | Promotion for students enrollment | 
 | Report of promotion for students enrollment | 15.05.2020 – 15.08.2020

## Slide 8
WP7 – MANAGEMENT Project management |  | 
7.1 | Project management meeting | 
 | Minutes of the meeting - UB in consultation with other partner institutions | 15.05.2020
7.2 | Steering committee meeting | 
 | Minutes of the meeting - UB in consultation with other partner institutions | 15.05.2020
7.4 | Day–to-day coordination of project activities | 
 | Report of day-to-day coordination - UB in consultation with other partner institutions | 15.05.2020
7.5 | Interim and final report meeting | 
 |  | 15.03.2020 – 15.06.2020
Notes: Project management and Steering committee meeting will be held in mid-May. Report of day-to-day coordination will be submitted aslo in mid-May.

## Slide 9
What should we do in the next six months? | to 15.05.2020
Established new and improved existing subjects | finish
Established new master programme | finish
Study visits EU university and analysis best practices | finish
Harmonization of the proposed changes | finish
Quality Assurance Committee meeting | once
Project website created and maintenance | constantly
Promotion material created | constantly
Project management meeting | once
Steering committee meeting | once
Notes: This slide provides the list of the activities that should be done in the next six months.
Quality Assurance Committee meeting, Project management meeting as well as Sterring Committese meeting in plan to occure once innext six months, while Project website created and maintenance and Promotion material created are performing permamnently.

## Slide 10: Events
2.5 Study visits EU university and analysis best practices
From project Aplication form “.. study stays with teachers and students from Serbian and Bosnian-Herzegovinian universities at EU countries’ and Macedonia’s universities... The goal ... is obtaining a perception of the teaching process at the universities (methodologies, pieces of equipment etc.) and the adoption of good practices in those countries.”
Proposal:
Study visit at the University in Bulgaria– mid-April, 2020 (13-14 April 2020)
Study visit at the University in Italy – end June or beginning of July 2020 (29 June to 1st July or 6-8 July 2020)
Study visit at the BOKU in Austria –September 2020 (28-30 September 2020 or 5-7 October 2020)
Consultative meetings of universities from B&H and Serbia (UB, UNS, UNI, UBL, UNSA)
Proposal
University of Belgrade – end Januar 2020 (24 Januar 2020) and/or
University of Novi Sad – mid March 2020 (12 March 2020)
Notes: To establish a new master program, syllabus of subjects and learning materials, it is necessary to hold 1-2 meetings of universities from Serbia and B&H.