## Slide 1: FINANCIAL STATEMENT
18-19 November 2019, Banja Luka

## Slide 2
Instructions
Final financial statement
Costs incurred&2nd Prefinancing
1. Staff costs
2-3. Travel Costs&Costs of Stay
4. Equipment Costs
5. Subcontracting Costs
Co-financing
Breakdown and Project Funding
Breakdown Staff and Travel Costs
Financial reporting

## Slide 3
for travel costs (travel tickets, boarding passes... )
PROOF OF PAYMENT
- for stay cost

## Slide 4
100% of SETOF grant
first pre-payment
50%
equipment
rest of the money
50%
50%
R E M I N D E R !
University of Belgrade- Cord SETOF
1st instalment of first pre-financing
2nd instalment of first pre-financing

## Slide 5
Institution | 1st instalment of first pre-financing SPENT
UB | 88.7%
UNS | no information
UNI | 39.3%
UBL | 14.2%
USA | 19%
INSZASUM | 80.1%
BOKU | no information
UNSCM | no information
UNIRC | 54.2%
FRI-BAS | 72.2%
The present situation!
In order to request
the 2nd instalment of first pre-financing
we need to spend over 90% of
the 1st instalment of first pre-financing
with evidence/proof.

## Slide 6
pre-financing payment of 50% of the maximum amount upon entry into force of the Agreement
second payment of 40% of the maximum amount if:
  at least 70% of the previous pre-financing installment is spent
  the statement of costs incurred and the request for payment is sent to EACEA
  the progress report on the implementation of the Action (Intermediate report) is sent to EACEA
balance of 10% upon the approval of the Final Report
R E M I N D E R !

## Slide 7: Financial statement- Cord- UNB
+EQ
72.2%

## Slide 8: Financial statement- P1- UNS
NO FINANCIAL STATEMENT

## Slide 9: Financial statement- P2- UNI
+EQ
42.5%

## Slide 10: Financial statement- P3- UBL
+EQ
46.7%

## Slide 11: Financial statement- P4- UNSA
49.3%
+EQ

## Slide 12: Financial statement- P5- INSZASUM

## Slide 13: Financial statement- P6- BOKU
NO FINANCIAL STATEMENT

## Slide 14: Financial statement- P7- UNSCM
NO FINANCIAL STATEMENT

## Slide 15: Financial statement- P8- UNIRC

## Slide 16: Financial statement- P9- FRI-BAS

## Slide 17: Financial statement - SETOF
+57.97% we must spent
(-46.2%EQ) = about 11%
70% SETOF

## Slide 18: NECESSARY! - spent more than 70% of the funds by March (out of 50% recived) to make request for the next tranches of 40% of the project