## Slide 1: Reporting and correspondence on the project
Tijana Vulević, Aleksandar Baumgertel

## Slide 2
Within the implementation of the SETOF project correspondence implies:
notification on the daily level (between all partners and partners and project coordinator) about all issues important for the realization of the project
review off all comunication between all partners in the project consortium (performed using the following forms: regular meetings, e-mails, worskshops and study visits).
SETOF project correspondence

## Slide 3
Project coordinator is in a regular contact with Executive Agency (EACEA) (through the project officier) and in contact with project partners who are implementing all activities and providing reports and other documentation.
The SETOF project has established mail adress (setof.admin@sfb.bg.ac.rs) for correspondence with project partners on the daily level.
The coorespondence between all beneficiers is provided in the 1st version of the Day to day correspondence (for the period 15 November – 1 July 2019).
SETOF project correspondence

## Slide 4
Appearance of SETOF project on the the Erasmus+ Project Results Platform (Nov. 2018)
The first pre-financing payment is done by donator – EACEA (November 2018).
Withdrawal of Aristotle University of Thessaloniki, Greece (AUTH) (Dec. 2018)
Kick-off meeting held on 13-14 December 2018 in Belgrade
Iinitiated activities on the Dissemination plan development (Dec. 2018)
SETOF project correspondence
Important notes regarding Day to day coordination (activ. 7.4)
Notes: where the funds will be transferred to the beneficiary institutions after signing the Partnership Agreements.

## Slide 5
Decision of consortium about replacement of the partner AUTH, Greece with the new beneficiary Mediterranea University of Reggio Calabria, Italy (Dec. 2018)
Request for partner replacement (Jan. 2019)
The first monitoring visit to the project conducted by the Head of the National Erasmus+ Office in B&H and project officer from B&H at the University of Banja Luka (Rectorate) (Feb. 2019)
Deloped dissemination plan, final draf, by the leader of WP5 (Feb. 2019)
SETOF project correspondence

## Slide 6
The official request for partner replacement and budget revision was sent to the project officer (March 2019)
Completed documentation for partner replacement sent to the project officer (April 2019)
Project officer approved signature of the Partnership Agreements (May 2019)
1st PMU meeting, 1st Steering Commitee meeting and Study visit in Innsbruck (May 2019) where during SC meeting 4th version of Dissemination plan is adopted
SETOF project correspondence

## Slide 7
Meeting between project coordinate and leader of WP5 – UNI (May 2019)
Project coordinator obtain access to the electronic version of the Technical implementation report (e-report) (Jun 2019)
GUIDE FOR FILLING IN Joint Declaration, Timesheet and Individual Travel Report (ITR)- 2nd version available on the project website (July 2019)
University of Belgrade and company „Mediavuk“ signed contract about development and maintenance the project website (July 2019)
SETOF project correspondence

## Slide 8
SETOF project correspondence
Delivery of the documentation for Financial report (ITR, TS, JD, financial statement) (September 2019)
Presentations and publications - SETOF flyer created by UNI (Sept. 2019)
Quality contol and monitoring plan, draft version, delopet by the UNIRC (Sept. 2019)
Workshop on bachelor and master curricula best practices in EU – Italy and Visit to the torrential catchments in SILA mountain – The ‘Bonis’ experimental catchment (UNIRC - CNR) (Sept. and Oct. 2019)

## Slide 9
SETOF project correspondence
1 st Quality Assurance Committee meeting in R. Calabria, Italy (Oct. 2019)
Regional Cluster Meeting on CBHE projects' impact in the Western Balkans, Albania, Durres (Oct. 2019)
Correcpondence regarding the equipment procurement, problems that faces B&H (Oct. 2019)

## Slide 10
SETOF project correspondence
Workshop on bachelor and master curricula best practices – North Macedonia (Oct. 2019)
Annexes of the Quality plan collecting from the partners (responsible persons of certain WP) (Nov. 2019)
Cluster meeting of CBHE curriculum development projects involving partners from Bosnia and Herzegovina organised by the The National Erasmus+ Office in Bosnia and Herzegovina (NEO BA) (Nov. 2019)

## Slide 11
Reporting within the SETOF project serve to track project progress within the Consortium, but also for the external monitoring performed by the National Erasmus Office (NEO) and EACEA.
Within SETOF project the ways of reporting includes:
Formal reporting by the Coordinator
including Progress and Final Reports, provides the necessary information to the Executive Agency to assure them that our project is implemented according to the Grant Agreement provisions and Guidelines for the Use of the Grant.
SETOF project reporting

## Slide 12
Internal reporting within the Consortium
where beneficiaries inform the coordinator about the technical progress on institutional implementation of the project and partners’ financial reports with declaration of expenses incurred accompanied with necessary supporting documents.
Reporting within QAC regarding Project implementation and deliverables where beneficiaries fullfil templates available as a part of Quality plan
Work package self-assessment report – Annex Q
Partner self-assessment report – Annex R
Check list for review of deliverables – Annex S
Internal project quality evaluation form – Annex T
Internal project quality evaluation report – Annex U
Reports as a output of realized project activities
SETOF project reporting
Notes: (define mail outputs/outcomes and indicators, challenges, changes to WP) (partners contributions, changes in project realization, financial matters)
(deliverable compliance with WP, activity description, etc.) used for partnership evaluation of the project.

## Slide 13
All reports should be written in English and provided to the Coordinator and appropriate project bodies (PMU, SC, QAC)
Financial report:
financial statement table - original excel file
supporting documents
(joint declarations, individual travel reports and project time sheets) as original hard copies, and
other supporting documents
(agendas, list of participants, boarding passes, travel orders, or any other document proving mobility or participation in some activities) as hard copies.
Internal REPORTING
Notes: The Technical reports should provide the clear picture on the progress of project activities, time and quality of deliverables and results, to what extent the progress indicators are achieved

## Slide 14
Internal REPORTING
Financial report
Budget heading: Travel costs and Cost of Stay:
Fulfilled and signed Individual Travel Report (ITR) (ANNEX III)
Certified copy of the working contract
Certified copy of the mobility from, mobility order or other documents according to the institutional internal rules
Certified copy of the travel ticket(s) invoices(s),
Certified copy of the accommodation(s) invoice(s),
Certified copy of the calculation of costs,
Copies of the boarding passes or copies of the passport pages with dates of departure and arrival,
Copy of the pay tool(s),
Certified copy(es) of the other invoices paid by traveler or institution,
Certified copy of the tax and social contribution document(s),
Certified copy of bank statement and/or receipt(s) as a proof of payment(s) (travel costs, accommodation costs, daily allowances, travel insurance, etc.)
Agendas,
Attendance lists,
Tangible outputs/products,
Minutes od meeting
Documentation for all budget headings is provided in the Guidlines for reporting and correspondence
Notes: Periodic internal quality control is ensured with: annual Work Progress Reports of each
project partner and annual Work Progress Summary Report, Work packages self-assessment
report, Partner self-assessment report, Technical and Financial reports.

## Slide 15
Technical report (e-report).
financial statements
declaration of honour
statistics and indicators - aims to gather statistical data and indicators of performance for the period covered by the reporting period (related to the trainings and mobilities)
table of achieved/planned results (one table per WP), with describing elements in Guidlines for reporting and correspondence (ANNEX II)
Activities carried out and indicators of achievement,
Planned activities and indicators for progress,
Any proposed changes (people involved, budget, remaining activities, …).
Notes: The Technical reports should provide the clear picture on the progress of project activities, time and quality of deliverables and results, to what extent the progress indicators are achieved

## Slide 16
Thank you for your attention!!!

## Slide 17
All events on the project are documented by different material available on the project website (www.setog/org) .
Type of event |  | 
Workshop, Study visit | Kick-off, SC, PMU, QAC meetings | Trainings
Study Visit and analysis best practices in EU countries, 16th May 2019 , Innsbruck, Austria Material: agenda, MoM, attten. list, gallery | Kick-off meeting on December 13-14th December 2018, Belgrade, Serbia Material: agenda, MoM, attten. list, presentations of institutions and work packages, gallery | /
Workshop on bachelor and master curricula best practices in EU- Italy, 30th of September 2019, R. Calabria, Italy Material: agenda, MoM, attten. List, | 1st Project Management Unit Meeting, 15th May 2019, Innsbruck, Austria Material: agenda, MoM, attten. List, presentations, galler | /
 | 1st Steering Committee Meeting, 17th May 2019, Innsbruck , Austria Material: agenda, MoM, attten. List | /
 | 1st Quality Assurance Committee meeting, 2nd October 2019, R. Calabria, Italy Material: agenda, MoM, attten. List | /